THEME 8

Socio-economic sciences and Humanities

Collaborative Project, Small or medium scale focused research project

GILDED Work Package One Report:

Stakeholder Advisory Groups and Research Dissemination

Project acronym: 		GILDED

Project full title: 	Governance, Infrastructure, Lifestyle Dynamics and Energy Demand:  European Post-Carbon Communities

Grant agreement no.: 	225383

Date:				16 July 2010

GILDED WP1 Progress Report

Executive Summary

This report addresses the WP1 Activities (Stakeholder Advisory Groups and Research Dissemination) for the first eighteen months of the GILDED FP7 research project. The objective of this work package is to ensure optimal information exchange and dissemination between researchers, key stakeholders, policy makers and the general public. This is being achieved through two primary activities: regional stakeholder advisory groups and dissemination of study findings to multiple audiences.

Stakeholder Advisory Groups have been set up by all five of the research partners (MLURI, IPSHAS, RuG, PIK and RIFCH/USB). Each advisory group includes a range of members, including representatives of local and regional government, businesses, charities, development trusts, scientists and citizen groups. The advisory groups have played a key role in evaluating the appropriateness of multi-country survey design for their home country and in providing input to WP2 (Energy Demand, Governance and Infrastructure).

The web-site was established by MLURI in February 2009. The site statistics generally demonstrate a steady increase in the number and geographic spread of visitors to the web-site. Although the majority of visitors are from Europe, visits to the web-site have come from every continent except Antarctica.

GILDED team members have presented (or been accepted to present in summer 2010) 35 papers and posters on the GILDED project at scientific and public events. It is expected that these papers will provide the foundation for peer reviewed journal articles, to be written in the second 18 months of the project.

WP1 tasks also include a policy pamphlet of final policy recommendations, final case study workshops in each partner country, and a joint international workshop. These tasks are expected to be undertaken in the final months of the GILDED project.

GILDED met the project milestone for the web-site of Month 2, but was somewhat delayed in holding the initial regional stakeholder advisory groups (initially projected for Month 2). It was decided by some teams not to hold advisory group meetings until draft research protocols were developed, so that advisory groups would have something on which to provide feedback. All regional advisory groups held their first meeting by Month 10, and will have held their second meetings by Month 23.

WP1: Stakeholder Advisory Groups and Research Dissemination

Introduction

This report addresses the Workpackage 1 (WP1) activities for the first eighteen months of the GILDED FP7 research project. The objective of this WP is to ensure optimal information exchange and dissemination between researchers, key stakeholders, policy makers and the general public. This is being achieved through two primary activities: regional stakeholder advisory groups and dissemination of study findings to multiple audiences (e.g. through giving presentations at conferences and stakeholder events).

The involvement of stakeholders in research has particular importance for a project focused on consumer demand, and on policy outcomes. Identifying the urban and rural dwellers’ perspectives on energy reduction and their consumption preferences would be difficult without the access and analytical perspectives of local and regional stakeholders. The role of these individuals is also highly important for ensuring the relevance and implementation of policy recommendations.

Research findings from the project are intended for multiple audiences: policy makers, stakeholder groups, the general public and the scientific community. These diverse audiences will be reached through targeted interactions, including a web-site, information sheets, press releases, a final policy pamphlet, case study workshops, joint international workshops, conference presentations and peer-reviewed journal articles.

The report follows the following structure: overview of the objectives for WP1, progress on tasks and progress on milestones. This WP progress report is the only official GILDED deliverable from this WP: the web-site is also a deliverable, but formally associated with WP7 Project Management.

Background: Objectives from Annex 1

The objectives for WP1 listed in Annex 1 are as follows:

- to facilitate the integration of policy makers and other stakeholders into the research process, ensuring locally relevant results and recommendations

- to optimise dissemination of research findings between researchers, key stakeholders, policy makers and the general public.

The description of work is as follows:

An advisory group will be established in each case study region, consisting of local and regional stakeholders (including policy makers) and members of the research team. This group will meet as a whole on an annual basis (starting at month two of the project), in order to review the process and guide subsequent steps. Members of the advisory group will meet with researchers throughout the year on an as needed basis. Specific roles of the advisory group include: identify the key factors limiting post-carbon transition in their region (WP2, WP3, WP4, WP5); provide background information on governance, technological and socioeconomic and cultural issues impacting on carbon use behaviours (WP 2, WP3); identify possible contacts for key informant interviews (WP2); identify carbon reduction activities occurring in the case study region, and advice on case study selection for WP4; provide feedback on work-package findings (WP2, WP3, WP4, WP5, WP6); disseminate study findings and policy recommendations to their respective agencies; meet with case study group annually to discuss progress; meet with researchers individually as necessary; participate in regional workshop at project end; meet with other members of the other consultative groups at international conference workshop at project end, to discuss comparative issues in policy implementation.

These objectives have been achieved to the degree expected for this stage of the research process. For example, each national team has formed an advisory group. These grounds have contributed to data collection for WP2, WP3, WP4 and in one case WP5, provided feedback on initial findings from WP2 and WP3 and disseminated findings to date to their respective organisations. It is anticipated that in the second half of the GILDED project, advisory group members will become more engaged in WP5 and WP6, have an even stronger role in knowledge dissemination, as the findings from the research are finalised.

The tasks for WP1 are used as headings in the following section. The full WP description, as presented in Annex 1, can be found in Appendix A.

Progress on Tasks

Task 1.1.1 Establish Advisory Group

Each national team has organised a stakeholder advisory group, all which have met at least once (see T.1.1.2).

The University of South Bohemia (RIFCH/USB) Advisory Group includes representatives from: an Energy consulting company, local NGOs (energy consulting, environmental issues), a photovoltaic systems business company, the main energy producers (ČEZ, E.On) in the region, a grocery chain store, the South Bohemian University, the Department of Environmental issues of Municipality of České Budějovice, the Municipality of Trhové Sviny and the Global Environment Facility of Czech Republic.

The University of Groningen (RuG) team includes: A sustainability policy adviser, an energy coordinator, a policy advisor planning, an advisor of spatial planning (all of the municipality of Assen), a policy advisor of the environmental federation of the province of Drenthe and an employee of the housing organization in Assen.

The Macaulay Land Use Research Institute (MLURI) advisory group members include: a Member of Scottish Parliament and two Scottish government policy researchers, the Development Manager of Huntly Development Trust, the Director of Aberdeen branch of SCARF (Save Cash And Reduce Fuel) (a publicly funded organisation focusing on energy reduction within the home), a Sustainability Scotland Network officer (a network of sustainable development officers and advocates from Scottish local authorities) and representatives from Aberdeen and Aberdeenshire Councils.

The Potsdam Institute for Climate Impact Research (PIK) members include for Potsdam: an employee of the city’s climate coordination group, the CEO of residential building cooperative, an employee of a municipal energy supplier, the chairman of the Energy Forum Potsdam, the chairwoman of the local solar club, an employee of the City’s Urban and Traffic development, faculty of department IV “Urban Planning”, responsible for bicycle development, and a member of the city’s council/head of the green party faction.  Members for Potsdam-Mittelmark include: County administration staff – communal business development, a member of the green party/chairwoman of a renewable energy group, a member of a communal eco-village in Belzig.

The Hungarian Academy of Sciences (IPSHAS) advisory group includes: the president of the Association of Agri-energetics and environment-management, the organiser of an organic market in Debrecen, the president of ‘Locals for the Habitat’, president of the Environmental Committee of the City Hall of Debrecen, a teach leading a Green Club at the Csokonai Vitéz Mihály’ secondary school, the director of the agency for Environmental, nature conservation and water management at Tiszántúl, the team leader for city maintenance of the City Hall of Debrecen and several members of the University of Debrecen Institute Faculty of Humanities, Department of Sociology and Social Policy and the University of Debrecen Institute Faculty of Agri-economy and Rural Development

T 1.1.2 Advisory group meetings

RIFCH/USB (Czech Republic)

First meeting of advisory group was held in February 2009 in České Budějovice. The stakeholders were asked for their suggestions about possibilities of CO2 emissions lowering and appropriate indicators we could focus on in our survey (WP3/4). The second meeting was organized in January 2010 again in České Budějovice. During the meeting the research team went through the GILDED questionnaires and asked the stakeholders to comment on the appropriateness of the questionnaires regard Czech cultural background. Preliminary results of WP3 interviews were presented to members of Advisory Group as well as summary of their suggestions and opinions from the previous meeting. Stakeholders were nicely surprised that their suggestions were accepted into our questionnaires and they also appraised the current form of questionnaires as adequate for use in the Czech case study areas.

RuG (The Netherlands)

The advisory group of Assen held their first meeting in September 2009. The meeting was held at the municipality of Assen.  At this meeting, the aim of the GILDED project was discussed. Preliminary results with regard to WP2 were discussed and the members of the advisory group provided feedback. The plans for WP3 and 4 were discussed as well. It was decided to hold the next meeting when results of WP3 and 4 can be presented, which will be around summer 2010.

MLURI (UK)

The MLURI advisory group members met for the first time in Aberdeen at a project launch held in April 2010. The first formal meeting was held in August 2009, where the preliminary findings of WP2 and WP3 were discussed, and feedback was given on the web-site. Six of the advisory group members also were also interviewed in June/July 2009 as part of the analysis of governance and infrastructure issues in relation to household energy use (WP2). A further MSAG meeting was held in April 2010, where members provided input to the construction of the agent-based model (WP5). The next advisory group meeting is planned for September 2010.

PIK (Germany)

The PIK  advisory group members met for the first time in Potsdam in June 2009 during a GILDED presentation evening. The presentations were also open for the interested public. Including 10 members of the GILDED stakeholder group; about 40 people participated in this event. Presentation included a general introduction of success factors for sustainable communities and a comparative study on climate-active cities in Germany. Following this, special issues related to the case of Potsdam were raised. GILDED’s main activities were presented and expected results discussed.

Two smaller, separate advisory group meeting have taken place in Potsdam-Mittelmark (Potsdam’s adjacent county). These were combined with regular meetings of the County’s Renewable Energy Group. Members of this group are administrative staff, engineers and energy advisors as well as NGO members. In the first meeting in May 2009, the GILDED project and its aim were presented. Several comments by SAG members during this occasion were included in the further selection of interviewees. During the second meeting in Potsdam-Mittelmark in March 2010, initial results of the qualitative and quantitative study of WP3/4 were presented and discussed.

The next PIK advisory group meeting – which will include both members from the urban and rural group – is planned for autumn 2010.

IPSHAS (Hungary)

The first formal IPSHAS- advisory group  meeting was held in June 2009, where the preliminary findings of WP2 were discussed. Some of the advisory group members were also interviewed in May/June 2009 as part of the analysis of governance and infrastructure issues in relation to household energy use (WP2). A further IPSHASadvisory group meeting is to be held in July 2010, where members will be asked to feed/back on the main findings of WP2 and preliminary results of WP3.

For photos of Advisory Group meetings see Appendix B.

Tasks 1.2.1 Web-site

The web-site was established by MLURI in February 2009. Current pages include an introduction to GILDED, information on GILDED research, an events calendar, energy saving tips (including the GILDED energy saving poster used in the quantitative survey), and a members’ only section which hosts the GILDED web-forum and documents for group exchange. The information on GILDED research is available in English, German, Hungarian and Czech (the Dutch team did not consider Dutch translations necessary). Translations were provided by the respective national teams. The first GILDED policy brief is currently available on the web-site; it is expected that all subsequent deliverables will also be posted there.

The site has been set up to track the number and geographical location of visitors, and whether the visitor navigated from a search engine, a referring site, or directly (i.e. typing in the site URL); but the software available does not record the type of institution visitors come from. The software automatically sends monthly reports to the coordinator (Nick Gotts) and project administrator (Lee-Ann Sutherland).

Summary Statistics of GILDED Web-site

| Month (from January 2009) | Visits | Visitors | Countries |
| --- | --- | --- | --- |
| January | 46 | 14 | 3 |
| February | 178 | 43 | 6 |
| March | 94 | 52 | 9 |
| April | 183 | 119 | 22 |
| May | 187 | 96 | 26 |
| June | 223 | 96 | 20 |
| July | 89 | 59 | 21 |
| August | 198 | 95 | 22 |
| September | 109 | 67 | 22 |
| October | 111 | 79 | 25 |
| November | 149 | 116 | 27 |
| December | 115 | 101 | 31 |
| January (2010) | 203 | 167 | 33 |
| February | 179 | 155 | 32 |
| March | 218 | 197 | 30 |
| April | 187 | 164 | 34 |
| May | 170 | 116 | 37 |

The site statistics generally demonstrate a steady increase in the number and geographic spread of visitors to the web-site. Although the majority of visitors are from Europe, visits to the web-site have come from every continent except Antarctica. The majority of recent visitors (71%) find the web-site through a search engine. The remainder go directly to the site (24%) or are referred through a link from another site (9%).

For reference see: www.gildedeu.org

A screen shot of the main GILDED web-page can be found in Appendix C.

T 1.2.2 Information sheets:

An information sheet describing the GILDED project was written early in 2009. It was translated into German, Czech and Hungarian, and made available to advisory group members and through the web-site. It contains a map of study sites, research objectives, project activities and dissemination plans.

Further information sheets are pending formalisation of research findings.

T 1.2.3 Press releases:

A press release developed at the beginning of the project was not picked up by the media. However, subsequent efforts have led to two on-line articles in Germany, and an article for Holyrood Magazine of the Scottish Parliament, in the UK. It is anticipated that attracting press interest will be easier once there are finalised research findings from early WPs.

T1.2.4-6 are planned for the final months of GILDED.

T 1.2.4 Policy Pamphlet: of final policy recommendations, to be circulated at project end.

T 1.2.5 Case study workshops at project end: One in each case study area for local residents, stakeholders and policy makers to express local recommendations and findings.

T 1.2.6 Joint international workshop specifically targeting policy makers and the EU level recommendations resulting from the project

T 1.2.7 Conference presentations

GILDED team members have been enthusiastically engaged in presenting the GILDED project and initial findings at scientific conferences and public events. The following is a list of papers and posters representing GILDED:

Altenburg, C. 2010. “Between culture and climate - developing climate-friendly urban strategies for Potsdam” Poster presentation at the 6th European Conference of Sustainable Towns and Cities, Dunkerque-France May 19-21.

Altenburg, C. 2010. “Putting “Public Participation & Climate Protection” into Practice: finding viable solutions for Potsdam”. Presentation at a Winter School in Beroun, Czech Republic, 31st March.

Altenburg, C. 2010. “Effective climate protection in European Communities: about concepts and methods on the path to a climate-friendly city”. Presentation at a regional workshop “Climate Protection and Energy”, Luckenwalde, 9th March.

Altenburg, C. 2009. “Climate Change and Municipalities – A global problem and local solutions“, 1st Municipal Climate Protection Conference, Brandenburg an der Havel, 12th October.

Altenburg, C. 2009.  “Success factors for sustainable cities”, Public Forum, Potsdam, 16th June.

Altenburg, C., V. Peters and P. Schmidt. 2009. “Governance and infrastructure in Potsdam concerning climate change”, Exhibition Science Market Potsdam, 11th July..

Craig,T.; Gotts, N.M.; Marshall, K.; Neely, C.L.; Sutherland, L.A. (2009) People power: Laying the foundations for a "post-carbon" society. Holyrood Magazine, Environment Supplement, 23rd March 2009.

Cudlínová, E. (Forthcoming). Presentation in section “Climate Change after Copenhagen” in international conference Ecological Integrity and Globalisation: Science, Human Behaviour, Public Policy and the Law organised by GEIG in Vancouver, Canada, June 27 – July 3, 2010.

Fischer, A., T. Craig and C. Galan-Diaz. (Forthcoming). “Climate change and energy consumption: behaviours and coping strategies”. Paper accepted for presentation to 21st IAPS conference: Vulnerability, Risk and Complexity: Impacts of Global Change on Human Habitats, Leipzig-Germany Jun 27 – July 2, 2010.

Gotts, N.M. (2009) ABMED: A prototype agent-based model of energy demand. European Social Simulation Association, (ESSA), 6th Conference, University of Surrey, Guildford, 14th-18th September 2009.

Gotts, N.M. (2009) The GILDED Project. In-Land Magazine, Autumn/Winter 2009, p32.

Gotts, N.M. GILDED: Governance, infrastructure, lifestyle dynamics and energy demand: a collaborative project within the topic: Socio-Economic Factors and Actors Shaping the "Post-Carbon" Society. PACT kick-off meeting Brussels, 2008-10-07

Gotts, N.M., Sutherland, L-A. and Polhill, J.G.. GILDED: Governance, infrastructure, lifestyle dynamics and energy demand: European Post-Carbon Communities PACT Mid-Term Assessment Meeting, Brussels, 2010-05-18

Gotts, N.M. (2009) The GILDED Project. In: Consultation on Scotland’s Energy Efficiency Action Plan, Scottish Government. (Contribution to policy formation)

Gotts, N.M.; Carnegie, P. (2009) Policy relevant agent-based modelling in the GILDED project. European Social Simulation Association, 6th Conference, University of Surrey, Guildford, 14th – 18th September 2009. (Poster) Note: won best poster award.

Gotts, N.M. (2009) The GILDED Project – Governance, infrastructure, lifestyle dynamics and energy demand: European post-carbon communities. All Energy, Aberdeen, 20th May 2009. (Handout)

Gotts, N.M.; Sutherland, L.A.; Cudlinova, E.; Kovach, I.; Reusswig, F.; Steg, E.M.; Carnegie, P. (2009) The GILDED Project – Governance, infrastructure, lifestyle dynamics and energy demand: European post-carbon communities. International Scientific Congress on Climate Change, Copenhagen, 10-12 March 2009. (Poster)

Kriel, A., Peters, V., Fischer, A., Megyesi B., and Vávra, J. (Forthcoming). “Social representations of energy use and global environmental change – an exploratory study across Europe” Paper accepted for presentation to 21st IAPS conference: Vulnerability, Risk and Complexity: Impacts of Global Change on Human Habitats, Leipzig-Germany June 27 – July 2, 2010.

Lapka, M., Vávra, J. “Culture and human system in landscape ecology” Paper presented on conference Culture and landscape, organised by CZ-IALE in Brno, Czech Republic, January 22, 2010

Lapka, M. (Forthcoming). “Subjective perception of objective global changes?” Paper accepted on conference organised by Department of Sociology, Faculty of Philosophy, University of Vilnius. Vilnius, Lithuania, June 10 – 12, 2010

Megyesi, B. Changing face of rural governance, a case study from Hungary, 17-21 August 2009., Vaasa, Finnland XXIInd conference of the ESRS.

Peters, V.: Results and outlook of the GILDED project, Workshop meeting, Council of Renewable Energies, Belzig, 8th March 2010.

Reusswig, F.: Municipal strategies for Climate Protection in Potsdam, Public Forum, Potsdam, 15th October 2009

Reusswig, F.: Podium Discussion – Energy Revolution, Film release, Potsdam, 18th March 2010.

Reusswig, F.: Climate Change and Cities, 3rd Congress of National Urban Planning, Essen, 24th June 2009.

Reusswig, F.: “Low Carbon Culture”, Summer Academy Beuth, Technical University Berlin, 8-12 July 2009.

Reusswig, F.: „Climate Policy as societal activation“, 11th National Congress for political Education, Halle an der Saale, 12th March 2009.

Reusswig, F.: Climate Change and Cities – what Municipalities can do.”, Workshop “Devising a municipal climate programme for Hanau, Haunau, Germany 13th May 2009.

Steg, L. Green Marketing. Presentation at the Green Spring Festival, Rotterdam, 20th of May 2010.

Steg, L. Psychology and energy saving. Presentation at the Sustainable Constructing Meeting. Dieren, 3rd of February 2010.

Sutherland, L.A.; Gotts, N.M. (2009) GILDED: governance, infrastructure, lifestyle dynamics and energy demand: European post-carbon communities. Open Doors, Macaulay Institute, June 2009. (Poster)

Van der Werff, E. & Steg, L. Factors influencing meat consumption. Presentation at the 8th Biennial Conference on Environmental Psychology Zurich, 6-9th September 2009.

Van der Werff, E. & Steg, L. Factors influencing meat consumption. Poster presentation at the 1st European Energy-Efficiency and Behaviour Conference, Maastricht the Netherlands, 18-20th of October 2009.

Van der Werff, E. Changing behaviour. Presentation at the Knowledge day for policy advisors of the Nature and environmental education organization. Arnhem, November 26th 2009.

Van der Werff, E. Energy consumption. Presentation for councillors and policy advisors of the province of Friesland. Earnewoude, June 2nd 2010.

Van der Werff, E. Energysavings and behavior. Presentation at an energysymposium of the province of Overijssel. Hardenberg, June 16th 2010.

T 1.2.8 Peer reviewed articles:

Forthcoming once WP findings are finalised.

Progress on Milestones

Milestones

M 1.1 Project web-site established (month 2)

M 1.2 Meetings of regional advisory groups (month 2, 13, 25, 35)

M 1.3 Regional workshops (month 34-35)

M 1.4 International workshop (month 36)

M 1.5 Final policy recommendation pamphlet circulated (month 36)

As described above, the project web-site was established in Month 2, and each team has held a regional stakeholder advisory group meeting within the first nine months of the project. While this represents a delay from the initial projections, it was felt by some teams that advisory group members would feel it was better use of their time if the advisors had some proposed methods and project findings on which to provide feedback. Stakeholder advisory group members have also contributed individually towards data collection for WP2.

Appendices

Appendix A:

Description of Workpackage 1 from Annex 1 of the GILDED Grant Agreement

B1.3.5 Work package descriptions

| Work package number | 1 | Start date or starting event: | Month 1 |
| --- | --- | --- | --- |
| Work package title | Stakeholder Advisory Groups and Research Dissemination |
| Activity Type | RTD |
| Participant number | 1 | 2 | 3 | 4 | 5 |
| Person-months per participant: | 5 | 5 | 5 | 5 | 6 |

Objectives to facilitate the integration of policy makers and other stakeholders into the research process, ensuring locally relevant results and recommendations to optimise dissemination of research findings between researchers, key stakeholders, policy makers and the general public.

Description of work (possibly broken down into tasks), and role of participants An advisory group will be established in each case study region, consisting of local and regional stakeholders (including policy makers) and members of the research team. This will group will meet as a whole on an annual basis (starting at month two of the project), in order to review process and guide subsequent steps. Members of the advisory group will meet with researchers throughout the year on an as needed basis. Specific roles of the advisory group include: identify the key factors limiting post-carbon transition in their region (WP2, WP3, WP4, WP5); provide background information on governance, technological and socioeconomic and cultural issues impacting on carbon use behaviours (WP 2, WP3); identify possible contacts for key informant interviews (WP2); identify carbon reduction activities occurring in the case study region, and advise on case study selection for WP5; provide feedback on work-package findings (WP2, WP3, WP4, WP5, WP6); disseminate study findings and policy recommendations to their respective agencies; meet with case study group annually to discuss progress; meet with researchers individually as necessary; participate in regional workshop at project end; meet with other members of the other consultative groups at international conference workshop at project end, to discuss comparative issues in policy implementation. Tasks T 1.1.1 Establish advisory group T 1.1.2 Advisory group meetings Dissemination of research findings will be ongoing throughout the project, and take the following forms: Tasks T 1.2.1 Web-site: established early in the project to facilitate communication between research teams, and act as a source of information on the project and findings for all target audiences T 1.2.2 Information sheets: will be derived from key deliverables from each workpackage, and disseminated to interested parties and via the project web-site. Fact sheets will be produced in the national language of the case study regions, with master copies translated into English and available on the web-site. T 1.2.3 Press releases: derived from fact sheets, will be circulated to local media on an ongoing basis throughout the project, informing members of the general public of topical issues and findings. T 1.2.4 Policy Pamphlet: of final policy recommendations, to be circulated at project end. T 1.2.5 Case study workshops at project end: One in each case study area for local residents, stakeholders and policy makers to express local recommendations and findings. T 1.2.6 Joint international workshop specifically targeting policy makers and the EU level recommendations resulting from the project T 1.2.7 Conference presentations. T 1.2.8 Peer reviewed articles: see other workpackages.

Deliverables (brief description and month of delivery) D7 Progress report (month 18) Milestones M 1.1 Project web-site established (month 2) M 1.2 Meetings of regional advisory groups (month 2, 13, 25, 35) M 1.3 Regional workshops (month 34-35) M 1.4 International workshop (month 36) M 1.5 Final policy recommendation pamphlet circulated (month 36)

Appendix B: Photographs from Stakeholder Advisory Group Meetings

PIK: First Stakeholder Advisory Group meeting in 
June 2009

IPS HAS: First Stakeholder Advisory Group Meeting

Appendix C: Screen Shot of GILDED web-site

Appendix D: Press Clippings for GILDED project activities

Märkische Allgemeine Zeitung 18.6.2009

http://www.maerkischeallgemeine.de/cms/beitrag/11536182/60709/Kommunale-Strategien-zum-Klimaschutz-Oekologische-Verhaltensluecke-FORUM.html

“Municipal Strategies of Climate Protection”

Märkische Allgemeine 20.05.2009

http://www.maerkischeallgemeine.de/cms/beitrag/11512849/60889/Fuenf-Vortraege-im-Arbeitskreis-Erneuerbare-Energien-International-und.html

“Five Presentations in the Working Group of Renewable Energies”

Holyrood Magazine (Scottish Parliament)

Holyrood Article Continued: